Team 1 : HEDROUG, LOUM, SAINT-MARTIN, LAINES, DIEYE

LOGICAL FRAMEWORK/ Activity Matrix

|  | Results chain | Indicators | Source and mean of verification | Assumptions |
| --- | --- | --- | --- | --- |
| Impact (Overall objective ) | Improve public health, environmental quality, and urban well-being in Bissau by reducing pollution and unmanaged waste through circular economy and recycling initiatives. |  |  |  |
| Outcome (Specific objective) | Establish an efficient and inclusive solid waste management system that reduces open dumping and burning, improves waste collection and recycling, and strengthens institutional coordination. |  |  |  |
| Outputs | 1. Circular economy plan and pilot recycling hubs created. 2. Improved waste collection and sorting in selected neighbourhoods. 3. Awareness and school programmes promoting proper waste disposal. 4. Municipal and community actors trained and equipped for sustainable waste management. |  |  |  |

Activity Matrix

| Outputs |  |
| --- | --- |
| 1. Circular economy plan and pilot recycling hubs created. 1.1. Conduct baseline studies and waste-flow analysis in targeted areas. 1.2. Develop the Circular Economy Implementation Plan in coordination with CMB ( (Bissau City Council) and UNEP (United Nations Environment Programme). 1.3. Identify and establish pilot recycling hubs (plastics, organic, metals). 1.4. Provide equipment and initial operational support for local cooperatives managing the hubs. 1.5. Monitor and evaluate the performance of pilot hubs for replication. |  |
| 2. Improved waste collection and sorting in selected neighbourhoods. 2.1 Provide new waste bins to households and public spaces. → Give people proper bins for separating their waste 2.2 Design a new waste management plan for target areas. → Create a plan with clear rules for waste separation and collection 2.3 Partner with recycling companies for waste processing. → Ensure that collected materials are properly recycled. |  |
| 3. Awareness and school programmes promoting proper waste disposal. 3.1 Design and roll-out of awareness campaigns: - Design of communication materials (flyers, posters, radio, social media). - Community events and clean-up campaigns. - Partnerships with local leaders and NGOs. 3.2 : Integration of waste education into schools: - Development of environmental modules. - Teacher training sessions. - Creation of school eco-clubs and “Clean School Day” events. 3.3 : Community engagement: - Training of “Green Ambassadors.” - Collaboration with parent–teacher associations. - Local media partnerships for ongoing messaging. 3.4 Monitoring and evaluation: Awareness surveys and feedback tools to measure behavioral change. |  |
| 4. Municipal and community actors trained and equipped for sustainable waste management. 4.1. Train municipal staff and community groups on waste sorting, collection, recycling and composting 4.2. provide equipment: PPE, bins, small tools, and appropriate collection vehicles 4.3. Establish or strengthen municipal waste units and basic monitoring systems 4.4. Raise community awareness through local campaigns and engagement of neighbourhood leaders 4.5. Partner with NGOs, recycling, businesses and informal collectors to improve practices |  |