Logical framework and activity marix

|  | Results chain | Indicator | Source and mean of verification | Assumptions |
| --- | --- | --- | --- | --- |
| Impact (Overall objective ) | Improve environmental health and living conditions in Bissau through a sustainable, efficient and socially inclusive solid waste management system | Quantitative: • Reduction of unmanaged waste in public areas by 30–40% within 3 years Increase in households with access to regular waste collection from baseline to 70%. Qualitative: • At least 70% of surveyed households report improved cleanliness and living conditions. | • Health statistics from local clinics/Ministry of Health. • Household surveys and community perception surveys. | Not applicable |
| Outcome (Specific objective) | Establish a Sustainable solid waste management system | Quantitative: • At least 80% of neighborhoods receive waste collection at the planned frequency • At least 85% of waste collection vehicles remain operational at any given time. Qualitative: • 70% of users and 75% of staff report satisfaction with service reliability. | • SWM unit administrative reports (staffing, performance). • Annual municipal budget and expenditure reports. • Activity monitoring database. | • Stable security and socio economic conditions in Bissau • Continuous political support from municipal authorities |

| Outputs | 1. Improve waste infrastructure and collection system 2. Strength institutional and technical capacity 3. Enhance community participation and environmental awareness 4. Improve financial management and | 1.Quantitative: • At least 20 functioning collection points, 3– 4 transfer areas, and 90% of planned collection routes operating as scheduled. Qualitative: • 70% of residents rate accessibility and cleanliness of collection points as "good" or "very good". 2.Quantitative: • 100 staff trained, with 60–70% applying new operational procedures after 6 months. Qualitative: • Managers report at least a 30% improvement in institutional performance and problem-solving capacity. 3.Quantitative: • Minimum 25 awareness activities conducted. + 50% of community members demonstrate correct waste practices (sorting, disposal, engagement). Qualitative: • 60% of community members show positive attitudes toward waste sorting and municipal services. 4.Quantitative: • 3 financial tools (budget templates, | Common sources of verification for all outputs： • SWM unit organizational structure documentation • Workshop reports and feedback forms • Attendance lists from events. • Social media analytics (views, shares) • School participation reports • Municipal financial reports and updated budgets • Site rehabilitation reports and photos • Medical check-up records from clinics | Assumptions for each outputs: 1. Communities accept the installation of new waste points 2. Institutional reforms supported by municipality leadership； Low staff turnover during the project period 3. Communities are willing to participate in awareness activities； Communication channels (radio, social media, events) remain accessible 4. Municipal authorities commit |
| --- | --- | --- | --- | --- |

|  | partnership for SWM 5. Improve the working condition (health and safe) for waste workers | cost-tracking tools, tariffs) updated. + 5 partnership agreements operational. Qualitative: • At least 70% of stakeholders report improved financial transparency and partnership effectiveness. 5.Quantitative: • 90% of workers equipped with appropriate PPE. + Reduction of workplace safety incidents by 40%. Qualitative: • 75% of workers report improved safety, dignity and comfort at work. |  | to adopting financial reforms； 5. Workers are willing to participate in training and health check-ups； Waste management companies cooperate with safety requirements |
| --- | --- | --- | --- | --- |

Activity Matrix

| 1. Improve waste infrastructure and collection system： 1.1 survey and assess existing waste collection points and transfer stations 1.1.1 visit sites, check equipment conditions, identify | Means What are the political, technical, financial, human and material resources required to implement these activities, e. g. staff, equipment, supplies, operational facilities, etc. | Assumptions 1. Communities accept the installation of new waste points： 1.1 |
| --- | --- | --- |

| priority areas 1.2 Rehabilitate and upgrade damaged collection points and small transfer areas. 1.2.1 Hire local contractors and supervise construction work. 1.3 Build new waste collection points in unserved neighborhoods. 1.3.1 Prepare simple designs and obtain local permits. 1.4. Strengthen waste collection equipment and ensure its proper management 1.4.1. Procure essential waste collection equipment (trucks, bins, tools) and replenish stocks 1.4.2. Establish a maintenance and repair system for equipment and facilities 1.4.3. Set up a monitoring system for equipment condition and availability 1.4.4. Plan and optimize collection routes to ensure regular coverage across all neighborhoods | Costs What are the action costs? How are they classified? (Breakdown in the Budget for the Action) |  |
| --- | --- | --- |
| 2. Strength institutional and technical capacity 2.1. Conduct structured capacity-building programs for local institutions 2.1.1. Assess existing technical and institutional |  |  |

| capacity gaps 2.1.2. Train municipal staff on technical solid waste management operations 2.1.3. Train staff on environmental and health aspects 2.2. Develop and implement standard operating procedures (SPO), for waste collection and transport 2.2.1. Draft and validate SOPs through workshops with municipal staff 2.2.2. Train field teams and supervisors on the use of the SOPs 2.2.3. Pilot the SOPs in selected neighborhoods and adjust based on feedback 2.3. Establish a dedicated SWM unit 2.3.1. Define the unit’s structure, roles, staffing needs, and mandate 2.3.2. Assign or recruit staff and provide basic operational training 2.3.3. Equip the unit with essential office and communication tools. 2.4. provide technical equipment and tools 2.4.1. Identify priority equipment needs based on |  |  |
| --- | --- | --- |

| operational gaps 2.4.2. Procure and distribute equipment to relevant teams 2.5. facilitate knowledge exchange and partnership 2.5.1. Organize peer-learning workshops with other municipalities or agencies 2.5.2. Establish collaborations with NGOs, universities, and regional SWM networks |  |  |
| --- | --- | --- |
| 3. Enhance community participation and environmental awareness 3.1 Establish a communication and community outreach team 3.1.1. Recruit or designate a media/outreach team responsible for awareness activities 3.2. Raise public awareness through targeted communication 3.2.1. Produce and disseminate educational materials on social media and in public spaces (short videos, posters, infographics about good waste practices) 3.2.2. Integrate waste management awareness sessions into school programs |  |  |

| (basic environmental education modules, interactive activities) 3.2.3. Organize community events to promote proper waste management (clean-up days, demonstration sessions, information booths) 3.3. Engage key influencers and community leaders 3.3.1. Train religious and traditional leaders to promote responsible waste practices 3.4 Explain to the population the goal of the project |  |  |
| --- | --- | --- |
| 4. Improve financial management and partnership for SWM 4.1 Review and update the city waste management budget. 4.2 Train municipal staff in basic accounting and cost tracking. 4.3 Create a simple fee system to help cover waste service costs. 4.4 Develop public–private partnership (PPP) agreements with local companies. 4.5 Prepare short financial reports and share results with the public. |  |  |
| 5. Improve the working condition (health and safe) for waste workers |  |  |

| 5.1 Do more control on the respect of the work conditions in the companies 5.2 Provide protective equipment and safety kits to waste workers. 5.3 Conduct health and safety training on waste handling and hygiene. 5.4 Rehabilitate sorting and collection sites with safe and clean facilities. 5.5 Organize regular medical check-ups for waste workers. 5.6 Formalize informal workers through cooperatives and fair contracts. |  |  |
| --- | --- | --- |