## Feuil1
Result chain | MEANS ( technical,financial, human and material ressources required to implemement these activities e.g. staff,equipment ,supplies ,operational facilities etc. | COSTS Detailed calculation + overall cost per activity | Time schedule (54 months project)
Activty 0 (Funds) |  |  | 6 months before the project starts
OUTPUT1 ( Adoption of circular economy and recycling practices by institutions and communities.)
activity 1.1 Provide technical support to local authorities for integrating circular economy principles into municipal policies and procurement guidelines |  |  | 3,5 year
if needed: subactivity 1.1.1 ( Analysis of existing municipal policies ) |  |  | 4 months (1 to 4 months)
subactivity 1.1.2 (Identification of opportunities for integration of the circular economy) |  |  | 4 months (3 to 6 months)
subactivity 1.1.3 (Development or revision of procurement policies and guidelines) |  |  | 8 months (5 to 12 months)
subactivity 1.1.4 (Institutional validation with local authorities) |  |  | 5 months (10 to 14 months)
subactivity 1.1.5 (Continuous technical support for implementation) |  |  | 30 months (13 to 42 months)
activity 1.2. ( Facilitate peer-to-peer exchanges between institutions already applying circular practices and new adopters) |  |  | 3 year
if needed subactivity 1.2.1 ( Identification of model institutions ) |  |  | 4 months (6 to 9 months)
subactivity 1.2.2 ( Organization of exchange visits or workshops ) |  |  | 22 months (9 to 30 months)
subactivity 1.2.3 ( Capitalisation des bonnes pratiques) |  |  | 19 months (18 to 36 months)
subactivity 1.2.4 ( Follow-up of adoption by new institutions) |  |  | 19 months ( 24 to 42 months)
OUTPUT2 ( Cleaner environments and better sanitation )
activity 2.1 ( Develop pilot collection systems in selected neighborhoods of Bissau) |  |  | 2,5 year
if needed subactivity 2.1.1 ( Selection of pilot districts ) |  |  | 4 months (6 to 9 months)
subactivity 2.1.2 (Design of the collection system (roads, equipment, roles ) |  |  | 6 months (9 to 14 months)
subactivity 2.1.3 ( Operational implementation of pilot systems) |  |  | 15 months (14 to 28 months)
subactivity 2.1.4 (Monitoring and adjustments of pilot systems )
activity 2.2. ( Train municipal workers and informal waste collectors in safe and hygienic waste handling practices.) |  |  | 2,9 year
if needed subactivity 2.2.1 ( Development of training modules ) |  |  | 5 months (8 to 12 months)
subactivity 2.2.2 ( Training sessions for municipal agents) |  |  | 19 months (12 to 30 months)
subactivity 2.2.3 (Informal Collector Training Sessions ) |  |  | 25 months (12 to 36 months )
subactivity 2.2.4 (Evaluation of acquired knowledge and recycling of training ) |  |  | 19 months (24 to 42 months
activity 2.3 ( Organize community-led clean-up days to encourage civic participation and environmental responsibility) |  |  | 3,2 year
if needed subactivity 2.3.1 ( Community Mobilization ) |  |  | 33 months (10 to 42 months)
subactivity 2.3.2 ( Logistical organization of cleaning days) |  |  | 31 months (12 to 42 months)
subactivity 2.3.3 ( Capitalization and reporting of results ) |  |  | 31 months (18 to 48 months)
OUTPUT3 ( Improved health quality ) |  |  | 41 months
activity 3.1. ( Design and deliver comprehensive training programmes for local authority staff and health educators on the links between sanitation, waste management, and public health)
if needed subactivity 3.1.1 ( Identification of training needs ) |  |  | 4 months (8 to 11 months)
subactivity 3.1.2 ( Development of training programs) |  |  | 6 months (11 to 16 months)
subactivity 3.1.3 ( Implementation of training) |  |  | 13 months (16 to 28 months)
subactivity 3.1.4 ( Post-training follow-up) |  |  | 13 months (24 to 36 months)
activity 3.2( Distribute personal protective equipment (PPE) and hygiene kits to informal waste collectors and households)
if needed subactivity 3.2.1 ( Identification of beneficiaries ) |  |  | 5 months (10 to 14 months)
subactivity 3.2.2 ( Purchase of PPE and hygiene kits) |  |  | 25 months (12 to 36 months
subactivity 3.2.3 (Distribution to beneficiaries ) |  |  | 29 months (14 to 42 months)
subactivity 3.2.4 (Tracking of use ) |  |  | 31 months (18 to 48 months)
activity 3.3. ( Collaborate with the Ministry of Health to monitor public health improvements linked to cleaner environments)
if needed subactivity 3.3.1 ( Definition of health indicators ) |  |  | 5 months (12 to 16 months)
subactivity 3.3.2 (Regular collection of data ) |  |  | 33 months (16 to 48 months)
subactivity 3.3.3 (Joint analysis and reports ) |  |  | 33 months (18 to 50 months)
subactivity 3.3.4 (Adjustment of corrective actions ) |  |  | 27 months (24 to 50 months)
OUTPUT4 ( Job opportunities created )
activity 4.1. ( Develop technical skills for waste collection and sorting among workers)
if needed subactivity 4.1.1 ( Definition of key skills ) |  |  | 3 months ( 12 to 14 months
subactivity 4.1.2 ( Development of technical modules) |  |  | 5 months (14 to 18 months)
subactivity 4.1.3 ( Development of technical modules ) |  |  | 19 months (18 to 36 months)
subactivity 4.1.4 (Certification or recognition of skills ) |  |  | 13 months (30 to 42 months)
activity 4.2( Employ local unemployed people to collect and treat wastes)
if needed subactivity 4.2.1 ( Identification and selection of beneficiaries ) |  |  | 5 months (18 to 22 months)
subactivity 4.2.2 (Implementation of contracts or employment mechanisms) |  |  | 5 months ( 22 to 26 months )
subactivity 4.2.2 (Deployment of collection and processing activities ) |  |  | 25 months (24 to 48 months)
subactivity 4.2.4 (Socio-economic monitoring of jobs created) |  |  | 25 months (30 to 54 months
activity 4.3. ( Train waste pickers, youth, and women in recycling and composting skills) |  |  | 31 months
if needed subactivity 4.3.1 ( Identification of target groups) |  |  | 5 months (18 to 22 months )
subactivity 4.3.2 ( Recycling training) |  |  | 17 months (22 to 38 months)
subactivity 4.3.3 ( Composting training) |  |  | 17 months (24 to 40 months)
subactivity 4.3.4 ( Post-training support) |  |  | 19 months (30 to 48 months)
activity 4.4. ( Support formation of waste cooperatives with legal and business training) |  |  | 31 months
if needed subactivity 4.4.1 ( Raising awareness of the cooperative approach) |  |  | 5 months (24 to 28 months)
subactivity 4.4.2 ( Legal support for the creation ) |  |  | 7 months (26 to 32 months)
subactivity 4.4.3 ( Training in management and entrepreneurship) |  |  | 13 months (30 to 42 months)
subactivity 4.4.4 ( Monitoring and support of cooperatives) |  |  | 19 months (36 to 54 months)
OUTPUT5 ( Population sensibilisation )
activity 5.1. ( Provide comprehensive training programs for local authority staff on modern waste management practices) |  |  | 13 months (6 to 18 months )
activity 5.2( Conduct door-to-door information sessions in target neighborhoods to promote household waste sorting) |  |  | 28 months (9 to 36 onths)
activity 5.3. ( Develop technical skills for waste collection and sorting among workers) |  |  | 19 months (12 to 30 months)
activity 5.4. ( Celebrate annual environmental events (e.g. World Environment Day, National Clean City Week) to maintain visibility and engagement) |  |  | 43 months (6 to 48 months)
OUTPUT6( Data accessibility and availability, research collaboration, and learning opportunities )
activity 6.1. ( Establish a data-sharing platform for waste management statistics and research findings) |  |  | 13 months (12 to 24 months)
activity 6.2( Partner with universities and research institutes to conduct applied studies on circular economy and waste valorization) |  |  | 25 monts (18 to 42 months)
activity 6.3. ( Develop technical skills for waste collection and sorting among workers) |  |  | 25 months (24 to 48 months)