THE DESIGN STEP AND THE LOGICAL FRAMEWORK APPROACH

IN COMPLIANCE WITH THE  GUIDELINES OF THE CALL  FOR PROPOSAL

| ANALYSIS PHASE | PLANNING PHASE |
| --- | --- |
| STAKEHOLDERS ANALYSIS : -Identifying & characterizing potential major stakeholders, - assessing their capacity | DEVELOPING LOGICAL FRAMEWORK MATRIX: -Defining project structure, testing its internal logic & risks, formulating measurable indicators of success |
| PROBLEM ANALYSIS : -Identifying key problems, constraints & opportunities -Identifying cause & effect relationships | TIME SCHEDULING for activities : -Determining the sequence dependency of activities -estimating their duration and assigning responsibility |
| OBJECTIVE ANALYSIS: - Developing solutions from the identified problems -Identifying means | RESOURCE SCHEDULING: Based on the activity schedule, developing means and a budget |
| STRATEGY ANALYSIS: -Identifying different strategies to achieve solutions -Selecting the most appropriate strategy | FINANCING PLAN: According to your overall budget, identifying all potential financial backers |